## Aravind
Feature Name | Task Description | Effort (Hours) | Actual Effort(Hours) | Estimated Start Date | Estimated End Date | Actual Start Date | Actual End Date | Status | Assigned To | Priority | Comments
Common UI
Dark Mode | Implement dark mode theme for the application. (hovering on the field is not readable) | 4 | [5 empty] | In-Progress | Aravind | Medium
Dashboard
Filters | Rework the filter functionality to support all required filters. |  |  |  |  | 2025-10-03 | 2025-10-03 | Completed | Aravind | High
Monthly Performance Trend | Fix the performance trend chart functionality. | 2 |  |  |  | 2025-10-01 | 2025-10-01 | Completed | Aravind | Medium
Quick Action | Implement quick action buttons for users. | 2 | [5 empty] | Yet to Start | Aravind | Low
Upcoming Tasks | Show tasks dynamically based on user data. | 4 | [5 empty] | Yet to Start | Aravind | Low
Deals
Deals Page | Ensure that after updating the deal, it closes automatically. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | Medium
Deal Updation Form UI Issues | Fix the UI layout and interactions in the deal updation form. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | High
Pagination | Resolve issues with pagination not working correctly. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | High
export | format : CSV,JSON | 1 |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | High
sorting | sorting the list by value,name | 0.5 |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Medium
search | add search functionality | 0.2 |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Medium
add the edit,delete,clone in the card |  | 1 |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Medium
Contacts
Import Contact Not Functional | Fix contact import functionality. | 2 |  |  |  | 2025-09-30 | 2025-09-30 | Completed | Aravind | High
Filter Not Working | Fix filtering issue in the contact list. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-10-03 | 2025-10-03 | Completed | Aravind | Medium
Search Broken | Fix the search functionality for contacts. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | High
Updating/Deleting Contacts | Resolve issues with updating/deleting contacts. | 2 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | Medium
Notes | Fix notes functionality. | 3 |  |  |  | 2025-10-03 | 2025-10-03 | Completed | Aravind | Medium
Activity form | same activity form for both contact and activity page | 1 |  |  |  | 2025-10-03 | 2025-10-03 | Completed | Aravind | Medium
delete and edit all contacts for admin | [5 empty] | 2025-10-09 | 2025-10-09 | Completed | Aravind | High
mention activity by which user | [5 empty] | 2025-10-09 | 2025-10-09 | Completed | Aravind | Medium
additional information | resolve the custom field display |  |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Medium
Call | remove the call button |  |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind | Low
Social Profiles
Email function | [5 empty] | 2025-10-09 |  | In-Progress | Aravind | High
email form (attach,image) | add attach functionality work |  |  |  |  | 2025-10-09 |  | In-Progress | Aravind | Medium
Analytics
filter option | implement filter functionality | 1 |  |  |  | 2025-10-03 | 2025-10-03 | Completed | Aravind | Medium
Auto-Refresh Not Working | Implement auto-refresh for analytics data. | 2 | [5 empty] | Yet to Start | Aravind | Low
Export Not Available | Implement export functionality for analytics. | 2 |  |  |  | 2025-10-03 | 2025-10-03 | Completed | Aravind | Medium
Customize Option Missing | Add customization options for analytics display. | 2 | [5 empty] | Yet to Start | Aravind | Medium
export | remove email option | 0.1 |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind | Low
remove auto refresh |  | 0.2 |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind | Low
overview | [8 empty] | Aravind
win rate analysis | working |  |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind
Pipeline | [8 empty] | Aravind
Pipeline health | stats in the health tab | [7 empty] | Aravind
performance | [8 empty] | Aravind
admin can view his and all users performance | [8 empty] | Aravind
filter (should list the user) | [8 empty] | Aravind
Activity
Insights Missing | Add insights into the activity module. | 2 | [5 empty] | Yet to Start | Aravind | Low
Templates Not Functional | Implement template creation/editing functionality. | 2 |  |  |  | 2025-09-29 | 2025-09-29 | Completed | Aravind | Medium
Export Not Working | Fix export functionality in activity. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | High
Filter Tab Scroll Issue | Fix the scroll issue in the filter tab. | 1 |  | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Completed | Aravind | Medium
delete activity | add delete functionality in the activity card | 1 |  |  |  | 2025-10-06 | 2025-10-06 | Completed | Aravind | Medium
Activity form UI | resolve the overlapping issue |  |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Low
should mention the user |  | 0.5 |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Low
contact visibility inconsistent | [5 empty] | 2025-10-09 | 2025-10-09 | Completed | Aravind | High
export (csv) user mentioned | csv should have the user filed |  |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | Medium
bulk operations | Export, Archive, delete |  |  |  |  | 2025-10-09 | 2025-10-09 | Completed | Aravind | High
all contact filter | lists the activity as table (timeline isn't helpful for all contacts) | [7 empty] | Aravind
0
Settings
User Management Issues | Resolve issues with user management functionality. | 4 |  |  |  | 2025-10-06 | 2025-10-06 | Completed | Aravind | High
Permissions Not Working | Fix permission setting issues. | 4 |  |  |  | 2025-10-06 | 2025-10-07 | Completed | Aravind | High
Integrations Missing | Implement integrations missing from system settings.(connected sucessfully) | 4 |  |  |  | 2025-10-01 | 2025-10-03 | In-Progress | Aravind | High
Custom Fields Not Functional | Resolve custom field functionality issue. (backend modals and logic has been implemented) | 4 |  | 2025-09-30 | 2025-10-01 | 2025-09-30 | 2025-10-03 | Completed | Aravind | Medium
Email Templates Broken | Fix broken email templates feature. | 2 |  |  |  | 2025-10-01 | 2025-10-01 | Completed | Aravind | High
System Configuration Not Available | Implement missing system configuration options. | 4 |  |  |  | 2025-10-01 | 2025-10-01 | Completed | Aravind | Medium
User Management
pagination | [5 empty] | 2025-10-10 | 2025-10-10 | Completed | Aravind | Medium
remove refresh | remove the unnecessary button | 0.1 |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind | Low
Custom Field
filter | filter by entity |  |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind | Medium
types — drop down and multi select | add types | [7 empty] | Aravind | Low
pagination | [5 empty] | 2025-10-10 | 2025-10-10 | Completed | Aravind | Medium
Email
usage | remove |  |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind | Low
template - category creation | ability to create new category |  |  |  |  | 2025-10-10 | 2025-10-10 | Completed | Aravind
subject dynamic content | merge field in subject | [7 empty] | Aravind
dynamic merge field | [8 empty] | Aravind
pagination
filter